## Sheet1
Stage | Number | Task | Weeks
|  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
PCB Design | 1 | Read related resources to get familiar with the diode clamped converters and PMSM drives. | Weeks 12: Revision and Prepare for Exam; Weeks 17: Exam; Weeks 30: Revision and Prepare for Exam; Weeks 35: Exam and Presentation
| 2 | Components selection according to the requirements, and order the components. | bar: Weeks 6; Weeks 9
| 3 | Draw the circuit schematic in KiCad. | bar: Weeks 6 to Weeks 8
| 4 | Plan PCB layout in KiCad, send project files to PCB factory for manufacturing. | bar: Weeks 8 to Weeks 11
Simulation | 5 | Whilst PCB is being manufactured, construct the diode clamped converter and the PMSM model. | bar: Weeks 4; Weeks 8 to Weeks 9
| 6 | Simulate the FOC algorithm and close the torque control loop. | bar: Weeks 11 to Weeks 13; Weeks 19 to Weeks 21
| 7 | Further accomplish the speed closed loop control in PLECS | bar: Weeks 14 to Weeks 15
Overall Testing | 8 | Solder and test the quality of the two PCBs. | bar: Weeks 21 to Weeks 22
| 9 | Construct the embedded C code in MCU. | bar: Weeks 23 to Weeks 26
| 10 | Use the PCB to drive a low power PMSM motor with full FOC. | bar: Weeks 27 to Weeks 29
Thesis Writing | bar: Weeks 26 to Weeks 32
Prepare for Presentation | bar: Weeks 33 to Weeks 34