## Sheet1
Stage | Number | Task | Weeks
|  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
PCB Design | 1 | Read related resources to get familiar with the diode clamped converters and PMSM drives. | Weeks 12: Revision and Prepare for Exam; Weeks 17: Exam; Weeks 30: Revision and Prepare for Exam; Weeks 35: Exam and Presentation
| 2 | Components selection according to the requirements, and order the components. | bar: Weeks 6; Weeks 9
| 3 | Draw the circuit schematic in KiCad. | bar: Weeks 6 to Weeks 8
| 4 | Plan PCB layout in KiCad, send project files to PCB factory for manufacturing. | bar: Weeks 8 to Weeks 11
Simulation | 5 | Whilst PCB is being manufactured, construct the diode clamped converter and the PMSM model. | bar: Weeks 4; Weeks 8 to Weeks 9
| 6 | Simulate the FOC algorithm and close the torque control loop. | bar: Weeks 10 to Weeks 12
| 7 | Further accomplish the speed and mechanical position closed loop control in PLECS | bar: Weeks 13 to Weeks 15
Overall Testing | 8 | Test the quality of PCB (especially the connection) with DC power source. | bar: Weeks 19
| 9 | Construct the embedded C code in MCU and validate simulation work with PCB connected to an RL load. | bar: Weeks 19 to Weeks 22
| 10 | Stretch target 1: Use the PCB to drive a low power PMSM motor with full FOC. | bar: Weeks 22 to Weeks 24
| 11 | Stretch target 2: Fully control the torque / speed / mechanical position of PMSM motor with a Qt based HMI on PC. | bar: Weeks 24 to Weeks 28
Thesis Writing | bar: Weeks 24 to Weeks 31
Prepare for Presentation | bar: Weeks 32 to Weeks 34
Deliverables |  |  | Weeks 6: D1; Weeks 11: D2; Weeks 14: D3; Weeks 19: D4; Weeks 22: D5; Weeks 31: D6; Weeks 35: D7
Milestone |  |  | Weeks 6: M1; Weeks 11: M2; Weeks 14: M3; Weeks 22: M4; Weeks 24: M5; Weeks 28: M6